FEDERAL ENERGY REGULATORY COMMISSION

WASHINGTON, DC 20426

June 22, 2012

OFFICE OF ENERGY PROJECTS

Project No. 2246-058 – California

Yuba River Project

Yuba County Water Agency

Curt Aikens, General Manager

Yuba County Water Agency

1220 F Street

Marysville, CA  95901-4740

- Subject:  Extension of Time for Filing the Initial Study Report for the Yuba River Project

Dear Mr. Aikens:

On April 24, 2012, you requested an extension of time to file the initial study report for the Yuba River Project from September 30, 2012 until December 3, 2012.  The purpose of the extension is to allow more time to provide information to the relicensing participants and for collaboration regarding second year studies.

Your request would allow completion of field work prior to development of the initial study report that should result in more productive discussions at the study report meeting.  In addition, granting your request would not affect the overall Process Plan and Schedule.  Therefore, your requested extension is granted and the Process Plan and Schedule is revised as follow:

| Responsible Entity | Pre-Filing Milestone | Date | FERC Regulation |
| --- | --- | --- | --- |
| YCWA | Initial Study Report | 12/3/12 | 5.15(c)(1) |
| All Stakeholders | Initial Study Report Meeting | 12/18/12 | 5.15(c)(2) |
| YCWA | Initial Study Report Meeting Summary | 1/2/13 | 5.15(c)(3) |
| All Stakeholders | Study Disputes/Requests to Modify Study Plan | 2/1/13 | 5.15(c)(4) |
| All Stakeholders | Response to Study Disputes/Requests | 3/3/13 | 5.15(c)(5) |
| FERC | Directors Study Plan Determination | 4/3/13 | 5.15(c)(6) |
| YCWA | Second Study Season | Spring/ Summer 2013 | 5.15(a) |

If you have any questions, please contact Alan Mitchnick at (202) 502-6074.

Sincerely,

Vince Yearick

Acting Director

Division of Hydropower Licensing

cc:  	Mailing List

Public Files