## Active Action Items
Action Item Log - Yuba County Water Agency's Yuba River Development Project Relicensing. Last update on 10/18/15 by JML.
Item No. | Source | Action Item | Status |  |  | Action Taken | Target Date | Date Complete | Responsible Party
|  |  | Open & Past Due | Open & in Future | Closed
Current Total Number of Open and Closed Items |  |  | 0 | 7 | 15
1 | 9/14/15 Recreation Meeting | Camping unit PAOT capacities: 5 PAOT per single site; 10 PAOT per double site; and 15-PAOT per triple site |  |  | X | Agreement | 2015-09-14 | 2015-09-14 | FS & YCWA
2 | 9/14/15 Recreation Meeting | Re-issue YCWA OH whitewater boating access proposal including rationale to RPs |  |  | X | Lynch e-mailed the proposal to RPs | 2015-09-17 | 2015-09-16 | Paquette
3 | 9/14/15 Recreation Meeting | E-mail to RPs Kelly Ridge suitable terrain map and approx. capacity options handout used during meeting, but with addition of acreages of each development area proposed. |  |  | X | Lynch e-mailed the map to RPs | 2015-09-17 | 2015-09-16 | Paquette
4 | 9/14/15 Recreation Meeting | Update Event Calendar to show 2016 rec meeting dates at FS in Nevada City, current agendas for rec meetings, and 10/1 or 10/2 Cottage Creek site visit: 10/5 Kelly Ridge site visit; and 10/21 Shadow Ridge site visit |  |  | X | Lynch updated the Event Calendar | 2015-09-18 | 2015-09-16 | Lynch
5 | 9/14/15 Recreation Meeting | Provide action item log and meeting handouts on Website to track rec meeting action items and agreements |  |  | X | Lynch provided after Lind reviewed | 2015-09-18 | 2015-09-21 | Lynch
6 | 9/14/15 Recreation Meeting | E-mail to RPs sketch of campsite layout YCWA used to estimate how many campsites could be accommodated at Kelly Ridge site |  |  | X | Lynch e-mailed sketch to FS | 2015-09-18 | 2015-09-18 | Paquette
7 | 9/14/15 Recreation Meeting | E-mail to RPs concept level layout for 15-20 campsites at Burnt Bridge site based on previous layout |  |  | X | Lynch e-mailed YCWA's initial draft concept plan showing layout | 2015-09-18 | 2015-09-24 | Horning
8 | 9/14/15 Recreation Meeting | Provide to YCWA and MHM FS' written comments/markups on the draft Cottage Creek Campground concept plan |  |  | X | Pierce e-mailed comments to YCWA and MHM | 2015-09-18 | 2015-09-18 | FS - Pierce
9 | 9/14/15 Recreation Meeting | Confirm MHM can attend either 10/1 or 10/2 visit to Cottage Creek site |  |  | X | On 9/29, Lynch advised Lind that MHM was not available. On 10/4, YCWA proposed one of the following for the site visit: 10/13, 10/14, 10/15 or 10/16. Lind to let Lynch know. Lind confirmed 10/16. | 2015-09-23 | 2015-09-29 | Rabone
10 | 9/14/15 Recreation Meeting | Provide to FS MHM Engineering's revision of the draft Cottage Creek Campground concept plan per FS' 9/14 comments/markups |  |  | X | On 10/4, Lynch advised Lind that MHM expected to have the revised map by 10/9, at which time Lynch would e-mail it to Lind. Lynch provided to Lind on 10/8. | 2015-09-25 | 2015-10-08 | Lynch
11 | 9/14/15 Recreation Meeting | Provide to YCWA comments on YCWA's proposal for OH whitewater boating access for discussion at 10/19 meeting |  |  | X | Steindorf e-mailed comments to Lynch. | 2015-10-19 | 2015-10-13 | Steindorf & FS
12 | 9/14/15 Recreation Meeting | Provide to YCWA proposal for whitewater boating access below NBB Dam and at New Colgate PH, and for shuttle upstream of NBB Reservoir for discussion at 10/19 meeting |  |  | X | Steindorf e-mailed comments to Lynch. | 2015-10-12 | 2015-10-13 | Steindorf
13 | 9/14/15 Recreation Meeting | Calculate how many shower stalls are needed at Kelly Ridge site based on assumption of 83 people per stall (coin-op/time limited stalls) |  | X |  |  | 2015-10-19 |  | Paquette
14 | 9/14/15 Recreation Meeting | Provide O&M costs for non-Project trails & trailheads (7 Ball, 8 Ball, Rebel Ridge & Old Camptonville Rd trails) |  |  | X | Lind provided e-mail to YCWA with information. | 2015-10-19 | 2015-10-06 | FS - Lind/Newell
15 | 9/14/15 Recreation Meeting | Provide cost estimates for YCWA responsibility by season for Oregon Creek Day Use Area |  |  | X | Lind provided e-mail to YCWA with information. | 2015-10-19 | 2015-10-06 | FS - Lind/Newell
16 | 9/14/15 Recreation Meeting | Provide to YCWA concept for Burnt Bridge Day Use Area and trail |  | X |  |  | 2015-10-19 |  | FS - Lind/Sullivan
17 | 9/14/15 Recreation Meeting | Provide details of FS proposed interpretive and education information program for inclusion in Rec Plan. |  | X |  |  | 2015-11-16 |  | FS - Lind/Newell
18 | 9/14/15 Recreation Meeting | Provide status of YCWA's discussions with Chy regarding access road to proposed Cottage Creek Day Use Area |  | X |  |  | 2015-11-16 |  | Rabone
19 | 9/14/15 Recreation Meeting | Provide status of YCWA's road use agreement with the County |  | X |  |  | 2015-11-16 |  | Rabone
20 | 9/14/15 Recreation Meeting | Provide feedback on size of Kelly Ridge RV dump station (FS standard on number of RVs per station) |  | X |  |  | 2015-11-16 |  | FS - Lind/Pierce
21 | 9/14/15 Recreation Meeting | E-mail to YCWA FS' written comments on YCWA's proposal regarding boat launch parking, including basis for additional 380 parking spaces |  |  | X | Lind provided e-mail to YCWA with information. | 2015-11-16 | 2015-10-06 | FS - Lind/Herbst
22 | 10/22/15 Cottage Creek Site Visit | E-mail to FS final Cottage Creek Campground concept plan based on agreements at the 10/22/15 site visit. |  | X |  |  | 2015-10-30 |  | Paquette
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50